## 03WBS
17WBS表
一、项目基本情况
项目名称 |  | BSI |  |  |  | 项目编号 |  | MN233
制作人 |  | BSI开发团队全部成员 |  |  |  | 审核人 |  | 刘骁
项目经理 |  | 刘骁 |  |  |  | 制作日期 |  | 2019-05-13
二、工作分解结构（R-负责 responsible； As-辅助 assist； I-通知 informed； Ap-审批 to approve）
分解代码 | 任务名称 | 包含活动 | 工时估算 | 人力资源 | 其他资源 | 费用估算 | 工期 | 刘骁 | 马欣宇 | 白丰硕 | 叶绵和 | 杨昱昊 | 杨志成 | 陈泽远 | 李寒松
1.1 | 项目准备 | 项目立项 | 4 | 2 |  |  | 2 | R | Ap | I | I | I | I | I | I
1.2 |  | 项目动员 | 2 | 2 |  |  | 1 | R | Ap | I | I | I | I | I | I
1.3 |  | 资金申请 | 2 | 2 |  |  | 1 | R | AP
1.4 |  | 硬件设备采购 | 3 | 3 | 摄像头及配套设备 | 10000 | 1 | R | Ap |  | AS |  |  | I
2.1 | 软件项目设计 | 开发里程碑确定 | 1 | 1 |  |  | 1 | R |  | I | I | I | I | I | I
2.2 |  | 制定开发规范 | 6 | 3 |  |  | 2 | AP |  | AS | R | I | I | I | I
2.3 |  | 制定开发计划 | 6 | 3 |  |  | 2 | AP |  | R | AS | I | I | I | I
2.4 |  | 制定质量计划 | 6 | 3 |  |  | 2 | AP |  | R | I | I | I | I | AS
2.5 |  | 制定发布计划 | 2 | 2 |  |  | 1 | R | AP | I | I | I | I | I | I
2.6 |  | 项目设计评审 | 4 | 4 |  |  | 1 | R | AS | AS | AS | I | I | I | I
3.1 | 需求分析 | 需求相关者确认 | 2 | 2 |  |  | 1 | AS | R | I | I | I | I | I | I
3.2 |  | 用户侧需求分析 | 6 | 2 |  |  | 3 | R | AP | I | I | I | I | I | I
3.3 |  | 开发用例设计 | 4 | 4 |  |  | 1 | R | AP | AS | AS | I | I | I | I
3.4 |  | 功能需求分析 | 6 | 3 |  |  | 2 | R |  | AS | AS
3.5 |  | 性能需求分析 | 6 | 3 |  |  | 2 | R |  | AS | AS | I | I | I | I
3.6 |  | 安全需求分析 | 6 | 3 |  |  | 2 | R |  | AS | AS | I | I | I | I
3.7 |  | 编写需求文档 | 9 | 3 |  |  | 3 | R |  | AS | AS | I | I | I | I
3.8 |  | 需求评审 | 2 | 2 |  |  | 1 | AS | R |  |  | I | I | I | I
4.1 | 概要设计 | 特殊概念确定 | 4 | 4 |  |  | 1 | AS | R | AS | I | I | I | I | I
4.2 |  | 系统环境确定 | 3 | 3 |  |  | 1 | R |  | AS | AS | I | I | I | I
4.3 |  | 系统业务层次设计 | 6 | 3 |  |  | 2 | R | AP |  | AS | I | I | I | I
4.4 |  | 系统技术架构设计 | 4 | 2 |  |  | 2 | R |  |  | R | I | I | I | I
4.5 |  | 系统硬件架构设计 | 4 | 2 |  |  | 2 | R |  |  | R | I | I | I | I
4.6 |  | 系统软件架构设计 | 6 | 2 |  |  | 3 | R |  |  | R | I | I | I | I
4.7 |  | 系统功能设计 | 4 | 3 |  |  | 1 | R | AS |  | AS | I | I | I | I
4.8 |  | 接口设计 | 4 | 2 |  |  | 2 | R |  |  | R | I | I | I | I
4.9 |  | 系统工作流程设计 | 2 | 2 |  |  | 1 | R |  |  | AS | I | I | I | I
4.10 |  | 数据结构设计 | 2 | 2 |  |  | 1 | R |  |  | R | I | I | I | I
5.1 | 详细设计 | 完成设计概述 | 3 | 3 |  |  | 1 | Ap | R |  | As
5.2 |  | 总体方案确认 | 3 | 3 |  |  | 1 | Ap | R |  | As
5.3 |  | 前端UI和交互设计 | 16 | 4 |  |  | 4 | Ap | R |  | As | As
5.4 |  | 登陆注册设计 | 12 | 4 |  |  | 3 | Ap | R |  | As | As
5.5 |  | 导航功能设计 | 16 | 4 |  |  | 4 | Ap | R |  | As | As
5.6 |  | 路况分析功能设计 | 12 | 4 |  |  | 3 | Ap | R |  | As | As
5.7 |  | 前端事故预测设计 | 12 | 4 |  |  | 3 | Ap | R |  | As | As
5.8 |  | 前端公共API服务设计 | 8 | 4 |  |  | 2 | Ap | R |  | As | As
5.9 |  | 前端用户中心设计 | 8 | 4 |  |  | 2 | Ap | R |  | As | As
5.1 |  | 身份认证设计 | 4 | 4 |  |  | 1 | Ap | R |  | As |  | As
5.11 |  | 后端导航服务设计 | 12 | 4 |  |  | 3 | Ap | R |  | As |  | As
5.12 |  | 后端路况分析设计 | 12 | 4 |  |  | 3 | Ap | R |  | As |  | As
5.13 |  | 后端事故预测设计 | 12 | 4 |  |  | 3 | Ap | R |  | As |  | As
5.14 |  | 后端公共API服务设计 | 12 | 4 |  |  | 3 | Ap | R |  | As |  | As
5.15 |  | 后端管理员后台设计 | 8 | 4 |  |  | 2 | Ap | R |  | As |  | As
5.16 |  | 大数据存储设计 | 12 | 4 |  |  | 3 | Ap | R |  | As |  | As
5.17 |  | 大数据分析设计 | 20 | 4 |  |  | 5 | Ap | R |  | As |  | As
5.18 |  | 大数据预测设计 | 8 | 4 |  |  | 2 | Ap | R |  | As |  | As
5.19 |  | 大数据数据整合设计 | 12 | 4 |  |  | 3 | Ap | R |  | As |  | As
5.2 |  | 数据采集功能设计 | 12 | 4 |  |  | 3 | Ap | R |  | As |  |  | As
5.21 |  | 硬件数据处理设计 | 12 | 4 |  |  | 3 | Ap | R |  | As |  |  | As
5.22 |  | 硬件数据传输设计 | 12 | 4 |  |  | 3 | Ap | R |  | As |  |  | As
5.23 |  | 详细设计确认 | 3 | 3 |  |  | 1 | Ap | R | I | As | I | I | I | I
6.1 | 软件编码 | 前端UI和交互编码实现 | 6 | 3 |  |  | 2 | I |  | Ap | As | R
6.2 |  | 登陆注册编码实现 | 6 | 3 |  |  | 2 | I |  | Ap | As | R
6.3 |  | 导航功能编码实现 | 9 | 3 |  |  | 3 | I |  | Ap | As | R
6.4 |  | 路况分析功能编码实现 | 9 | 3 |  |  | 3 | I |  | Ap | As | R
6.5 |  | 前端事故预测编码实现 | 9 | 3 |  |  | 3 | I |  | Ap | As | R
6.6 |  | 前端公共API服务编码实现 | 9 | 3 |  |  | 3 | I |  | Ap | As | R
6.7 |  | 前端用户中心编码实现 | 12 | 3 |  |  | 4 | I |  | Ap | As | R
6.8 |  | 身份认证编码实现 | 6 | 3 |  |  | 2 | I |  | Ap | As |  | R
6.9 |  | 后端导航服务编码实现 | 9 | 3 |  |  | 3 | I |  | Ap | As |  | R
6.1 |  | 后端路况分析编码实现 | 9 | 3 |  |  | 3 | I |  | Ap | As |  | R
6.11 |  | 后端事故预测编码实现 | 9 | 3 |  |  | 3 | I |  | Ap | As |  | R
6.12 |  | 后端公共API服务编码实现 | 12 | 3 |  |  | 4 | I |  | Ap | As |  | R
6.13 |  | 后端管理员后台编码实现 | 6 | 3 |  |  | 2 | I |  | Ap | As |  | R
6.14 |  | 大数据存储编码实现 | 6 | 3 |  |  | 2 | I |  | Ap | As |  | R
6.15 |  | 大数据分析编码实现 | 15 | 3 |  |  | 5 | I |  | Ap | As |  | R
6.16 |  | 大数据预测编码实现 | 9 | 3 |  |  | 3 | I |  | Ap | As |  | R
6.17 |  | 大数据数据整合编码实现 | 9 | 3 |  |  | 3 | I |  | Ap | As |  | R
6.18 |  | 数据采集功能编码实现 | 15 | 3 |  |  | 5 | I |  | Ap | As |  |  | R
6.19 |  | 硬件数据处理编码实现 | 15 | 3 |  |  | 5 | I |  | Ap | As |  |  | R
6.2 |  | 硬件数据传输编码实现 | 15 | 3 |  |  | 5 | I |  | Ap | As |  |  | R
7.1 | 单元测试 | 前端UI+交互单元测试 | 20 | 2 |  |  | 10 | I |  | Ap |  | As |  |  | R
7.2 |  | 登录注册单元测试 | 10 | 2 |  |  | 5 | I |  | Ap |  | As |  |  | R
7.3 |  | 前端导航单元测试 | 15 | 2 |  |  | 7.5 | I |  | Ap |  | As |  |  | R
7.4 |  | 前端路况分析单元测试 | 15 | 2 |  |  | 7.5 | I |  | Ap |  | As |  |  | R
7.5 |  | 前端事故预测单元测试 | 15 | 2 |  |  | 7.5 | I |  | Ap |  | As |  |  | R
7.6 |  | 前端公共API服务单元测试 | 20 | 2 |  |  | 10 | I |  | Ap |  | As |  |  | R
7.7 |  | 用户中心单元测试 | 20 | 2 |  |  | 10 | I |  | Ap |  | As |  |  | R
7.8 |  | 后台管理单元测试 | 15 | 2 |  |  | 7.5 | I |  | Ap |  | As |  |  | R
7.9 |  | 后端身份认证单元测试 | 15 | 2 |  |  | 7.5 | I |  | Ap |  |  | As |  | R
7.10 |  | 后端路径规划单元测试 | 15 | 2 |  |  | 7.5 | I |  | Ap |  |  | As |  | R
7.11 |  | 后端路况分析单元测试 | 15 | 2 |  |  | 7.5 | I |  | Ap |  |  | As |  | R
7.12 |  | 后端事故分析单元测试 | 20 | 2 |  |  | 10 | I |  | Ap |  |  | As |  | R
7.13 |  | 后端公共API服务单元测试 | 20 | 2 |  |  | 10 | I |  | Ap |  |  | As |  | R
7.14 |  | 后端用户中心单元测试 | 15 | 2 |  |  | 7.5 | I |  | Ap |  |  | As |  | R
7.15 |  | 分析数据存储单元测试 | 20 | 2 |  |  | 10 | I |  | Ap |  |  | As |  | R
7.16 |  | 黑点分析单元测试 | 35 | 2 |  |  | 17.5 | I |  | Ap |  |  | As |  | R
7.17 |  | 黑点预测单元测试 | 35 | 2 |  |  | 17.5 | I |  | Ap |  |  | As |  | R
7.18 |  | 数据整合单元测试 | 35 | 2 |  |  | 17.5 | I |  | Ap |  |  | As |  | R
7.19 |  | 后台管理单元测试 | 15 | 2 |  |  | 7.5 | I |  | Ap |  |  | As |  | R
7.20 |  | 数据采集模块单元测试 | 20 | 2 |  |  | 10 | I |  | Ap |  |  |  | As | R
7.21 |  | 数据预处理模块单元测试 | 20 | 2 |  |  | 10 | I |  | Ap |  |  |  | As | R
7.22 |  | 数据回传模块单元测试 | 20 | 2 |  |  | 10 | I |  | Ap |  |  |  | As | R
8.1 | 集成测试 | 数据采集系统集成测试 | 8 | 3 |  |  | 2 | I | I | Ap |  |  | As | As | R
8.2 |  | 大数据系统与数据采集集成测试 | 8 | 3 |  |  | 2 | I | I | Ap |  |  | As | As | R
8.3 |  | 大数据系统节点集成测试 | 10 | 3 |  |  | 3 | I | I | Ap |  |  | As |  | R
8.4 |  | 后台与大数据系统集成测试 | 10 | 3 |  |  | 3 | I | I | Ap |  |  | As |  | R
8.5 |  | 前端与后台集成测试（客户WEB端） | 15 | 5 |  |  | 3 | I | I | Ap |  | As | As |  | R
8.6 |  | 前端与后台集成测试（客户Android端） | 15 | 5 |  |  | 3 | I | I | Ap |  | As | As |  | R
8.7 |  | 前端与后台集成测试（客户IOS端） | 15 | 5 |  |  | 3 | I | I | Ap |  | As | As |  | R
8.8 |  | 前端与后台集成测试（管理员WEB端） | 15 | 5 |  |  | 3 | I | I | Ap |  | As | As |  | R
9.1 | 系统测试 | 集成测试：功能测试 | 9 | 3 |  |  | 3 | Ap | I |  |  | I | As |  | R
9.2 |  | 系统测试：兼容性测试 | 9 | 3 |  |  | 3 | Ap |  |  | I |  |  | As | R
9.3 |  | 系统测试：部署测试 | 9 | 3 |  |  | 3 | Ap | I | As |  | I |  |  | R
9.4 |  | 系统测试：安全测试 | 18 | 3 |  |  | 6 | Ap |  |  | I |  | As |  | R
9.5 |  | 系统测试：性能测试 | 9 | 3 |  |  | 3 | Ap | I |  |  | I |  | As | R
9.6 |  | 系统测试：压力测试 | 9 | 2 |  |  | 4.5 | Ap |  | As | I |  |  |  | R
10.1 | 验收测试 | 功能测试 | 10 | 4 |  |  | 2.5 | Ap | I |  | I | As | As | As | R
10.2 |  | 稳定性测试 | 4 | 2 |  |  | 2 | Ap |  | I | I | I | I | As | R
10.3 |  | 数据接口测试 | 4 | 4 |  |  | 1 | Ap |  | I | I | As | As | As | R
10.4 |  | 内部兼容性测试 | 5 | 3 |  |  | 1.6667 | Ap |  | I | I | R | R | I | As
10.5 |  | 性能测试 | 10 | 4 |  |  | 2.5 | Ap |  | I | I | As | As | As | R
10.6 |  | 应用安全测试 | 6 | 2 |  |  | 3 | Ap | I | R | I | I | I | I | As
10.7 |  | 易用性测试 | 4 | 4 |  |  | 1 | Ap | I | R | I |  | I |  | As
10.8 |  | 外部兼容性测试 | 5 | 2 |  |  | 2.5 | Ap |  | I | I | I | I | R | As
10.9 |  | 可维护性测试 | 6 | 4 |  |  | 1.5 | Ap |  | I | I | As | As | As | R
10.1 |  | 可扩充性测试 | 4 | 4 |  |  | 1 | Ap |  | I | I | As | As | As | R
10.11 |  | 用户文档检查 | 10 | 7 |  |  | 1.4286 | Ap | R | As | As | As | As | As | As